## Defect_tracker
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Backend1 | 2026-02-09 | Dataset contained inconsistent date formats and missing values during preprocessing. | Sprint 1 | Backend Team | Data Issue | Cleaned dataset, standardized column names, converted to datetime format. | 2026-02-10 | Closed | Issue fixed during data preprocessing stage
2 | Backend2 | 2026-02-12 | Invalid processing times found where decision date occurred before received date. | Sprint 1 | Backend Team | Data Validation Error | Removed incorrect rows and validated date relationships. | 2026-02-13 | Closed | Added validation rules
3 | Backend3 | 2026-02-14 | Outliers detected in processing time affecting distribution reliability. | Sprint 1 | Backend Team | Data Quality Issue | Applied IQR based outlier handling and capped extreme values. | 2026-02-15 | Closed | Improved dataset reliability
4 | Backend3 | 2026-02-22 | Difficulty identifying meaningful patterns from raw visa processing data. | Sprint 2 | Backend Team | Analysis Issue | Generated distribution plots, boxplots and correlation heatmap. | 2026-02-23 | Closed | Helped derive feature insights
5 | Backend4 | 2026-02-26 | Lack of meaningful features for machine learning model training. | Sprint 2 | Backend Team | Feature Engineering Issue | Created derived time features such as year, month, quarter and seasonal categories. | 2026-02-27 | Closed | Improved model input quality
6 | Backend4 | 2026-02-28 | High dimensional categorical features affecting model efficiency. | Sprint 2 | Backend Team | Modeling Issue | Applied encoding and aggregated country/state level processing statistics. | 2026-03-01 | Closed | Reduced dimensionality
7 | Backend6 | 2026-03-07 | Need for structured machine learning pipeline for prediction workflow. | Sprint 3 | Backend Team | Architecture Issue | Implemented preprocessing pipeline and trained baseline Random Forest model. | 2026-03-09 | Closed | Improved reproducibility
8 | Backend7 | 2026-03-12 | Model evaluation required consistent performance metrics. | Sprint 3 | Backend Team | Model Evaluation Issue | Evaluated models using MAE, RMSE and R² metrics. | 2026-03-13 | Closed | Best performing model selected
9 | Backend8 | 2026-03-14 | Repository structure not organized causing difficulty in reproducibility. | Sprint 3 | Backend Team | Development Issue | Structured repository, added requirements file and resolved Git conflicts. | 2026-03-15 | Closed | Repository standardized
10 | Backend9 | 2026-03-20 | Trained ML model needed to be exposed as a prediction API service. | Sprint 4 | Backend Team | Integration Issue | Designed REST API architecture using FastAPI. | 2026-03-20 | Closed | API endpoints implemented
11 | Frontend1 | 2026-03-22 | Difficulty connecting frontend input fields with backend API response. | Sprint 4 | Frontend Team | Integration Bug | Implemented API integration and response formatting. | 2026-03-23 | Closed | Interface functioning correctly
12 | Both Teams | 2026-03-26 | Deployment environment compatibility issues during cloud setup. | Sprint 4 | Both Teams | Deployment Issue | Created requirements file and configured cloud environment. | 2026-03-28 | Closed | Application deployed successfully